## Gantt chart 26-05-21
Activities that have been successfully completed with milestone date marked in yellow
Activities that are in progress with key milestone dates marked in yellow
Key milestone dates at which significant achievement is expected, where the indicated number is associated with the time of the event for the international knowledge-sharing workshop and research conference to be hosted by (1) University of Ibadan (Nigeria), (2) Catholic University of Cameroon (Cameroon), (3) & (4) INES-Ruhengeri (Rwanda)
End of the project implementation and wrap-up
Activity | Y1 (2019-2020) | [11 empty] | Y2 (2020-2021) | [11 empty] | Extension period: Oct-Dec 2021
| Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
| Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Activity 1: Signing of the contract between the Royal Academy of Engineering and the hub university | bar: Q1 Oct to Q1 Dec
Activity 2: Signing of the MoUs between the hub university and each partner university | bar: Q1 Oct to Q1 Dec
Activity 3: Design of a website for the activities of the project | bar: Q1 Oct to Q1 Dec
Activity 4: Management of the website for the activities of the project | bar: Q4 Nov
Activity 5: To establish the MoUs between the hub university and as many local industries as possible (academia-industry linkage) | bar: Q1 Nov; Q4 Nov
Activity 6: To establish the MoUs between each spoke university and as many local industries as possible (academia-industry linkage) | bar: Q1 Nov; Q4 Nov
Activity 7: To undertake staff secondments from the hub university into local industries and to receive industrial secondees into the hub university | bar: Q1 Nov; Q4 Nov
Activity 8: To undertake staff secondments from each spoke university into local industries and to receive industrial secondees into each spoke university | bar: Q1 Nov; Q4 Nov
Activity 9: To organise and host the first international knowledge-sharing workshop at University of Ibadan (spoke university, Nigeria), focusing on teaching and research activities in Civil Engineering | bar: Q1 Nov
Activity 10: To organise and host the second international knowledge-sharing workshop at Catholic University of Cameroon (spoke university, Cameroon), focusing on teaching and research activities in Civil Engineering | Q2 Feb: 2
Activity 11: To organise and host the third international knowledge-sharing workshop at INES-Ruhengeri (hub university, Rwanda), focusing on teaching and research activities in Civil Engineering | Q4 Jul: 3
Activity 12: To purchase the laboratory equipment in support of strengthening education and research within the hub university and each spoke university | bar: Q4 Nov
Activity 13: To enable researchers within the hub university and each spoke university to carry out research visits to other research-led institutions in sub-Saharan Africa | bar: Q4 Nov
Activity 14: To organise and host an international research conference at INES-Ruhengeri (hub university, Rwanda), followed by a summative evaluation of the project implementation | Q4 Nov: 4